# Meeting Summary - Technical Analysis

## Calares OMS Cloud Migration Discussion

Date:: May 20, 2026

## Executive Summary

Discussion regarding migration of Calares' Sterling OMS from on-premise to IBM SaaS cloud environment, including cost analysis, implementation timeline, and technical considerations.

## Key Deliverables

### 1. **Cloud Migration Implementation**

Scope:: Full Sterling OMS migration to IBM SaaS platform

Estimated Cost:: $1.0M - $1.5M (one-time implementation)

Timeline:: 3-6 months implementation period

Components:

Sterling OMS platform migration

Customization untangling and refactoring

Integration testing and validation

Knowledge transfer to functional analysts

### 2. **Annual Licensing & Support**

Current On-Premise Cost:: ~$547K/year (renewal September 1st)

Proposed SaaS Cost:: ~$825K/year (50% uplift)

License Coverage:: 20.5-21 million order lines

Includes:: Three part numbers (Call Center, Sterling OMS, bulk space allocation)

### 3. **Partner Support Services**

Current Annual Spend:: ~$230K with Lightwell

Proposed Budget:: $100K/year for ongoing partner support

Rationale:: Reduced need with IBM direct support access

### 4. **Hardware Considerations**

Current:: On-premise Linux servers

Future:: Eliminated with SaaS migration

Estimated Savings:: $2.5M - $3M over 5-year lease term

Infrastructure Team:: In-house team currently manages Linux environment

## Timeline & Milestones

### Immediate (Current State)

Issue:: Web.xml configuration problems blocking deployment

Status:: Patches introduced breaking changes

Action Required:: Technical call with Lightwell to resolve deployment blockers

Stakeholders:: Tony, Kathy (technical lead for OMS), Angie, Sandy

### Short-term (Next 7 Weeks)

Renewal Decision:: September 1st deadline approaching

Cost Analysis:: Finalize hardware costs and actual order line volumes

Proposal Development:: Detailed scoping with IBM Expert Labs team

### Implementation Phase (3-6 Months)

Month 1-2:: Environment assessment and customization analysis

Month 3-4:: Migration execution and testing

Month 5-6:: Validation, training, and cutover

Parallel Running:: 1-year grace period where on-premise runs at no charge during cloud adoption

### Post-Implementation

Year 1:: Stabilization period with potential for rollback if needed

Year 2+:: Consider additional modules (Store module, Intelligent Promising/SIP)

Ongoing:: Quarterly business reviews and optimization

## SWOT Analysis

### Strengths

**Existing Infrastructure Knowledge**

Team familiar with Sterling OMS functionality

Functional analysts (Sandy, Sean, Lim) already trained

Established processes and workflows

**IBM Direct Support Access**

Direct access to Sterling support tickets

Functional question support included in SaaS

Reduced dependency on third-party partners

**Upgrade Management**

IBM handles all upgrades and patches

No manual deployment process required

Eliminates current web.xml configuration issues

**Risk Mitigation**

1-year parallel running period

Ability to rollback to on-premise if needed

No forced commitment beyond evaluation period

### Weaknesses

**Higher Annual Costs**

50% increase in software licensing ($547K â†’ $825K)

Net savings only ~$125K/year after hardware elimination

Long ROI payback period on $1-1.5M implementation

**Implementation Complexity**

Customization untangling required

Potential impact on integrated systems

3-6 month disruption to business operations

**Current Technical Issues**

Unresolved web.xml deployment problems

Patch management challenges

Support ticket delays and back-and-forth

**Resource Constraints**

Memorial Day rush timing pressure

Limited technical staff (Kathy covers multiple products)

Functional analysts not reducing FTE needs

### Opportunities

**Additional Modules**

Store module for HD orders and enhanced flexibility

Intelligent Promising (SIP) for expected arrival dates

E-commerce feature enhancements

**Operational Efficiency**

Eliminate manual deployment processes

Reduce partner dependency over time

Faster issue resolution with direct IBM support

**Scalability**

Cloud-native architecture

Easier capacity adjustments

Modern platform for future growth

**Technical Debt Reduction**

Force customization cleanup

Standardize on best practices

Improve system maintainability

### Threats

**Migration Risk**

Potential business disruption during 3-6 month implementation

Integration failures with other systems

Data migration challenges

**Cost Overruns**

Implementation could exceed $1.5M estimate

Hidden customization complexity

Extended timeline increasing costs

**Vendor Lock-in**

Increased dependency on IBM SaaS platform

Limited control over upgrade timing

Potential future price increases

**Change Management**

Team resistance to new platform

Learning curve for cloud-based operations

Business partner adaptation required

## Technical Considerations

### Current Environment

Platform:: Linux servers (on-premise)

Order Volume:: 20.5-21M order lines annually

Integration:: AS/400 with IBM i (core retail/Ear key system)

Support Model:: Lightwell partner + in-house infrastructure team

### Migration Requirements

**Customization Assessment**

Identify all custom code and configurations

Determine what can be eliminated vs. must be migrated

Impact analysis on downstream systems

**Integration Points**

Core retail system connections

E-commerce platform integrations

Third-party system interfaces

**Data Migration**

Historical order data

Configuration and setup data

User accounts and permissions

**Testing Strategy**

Functional testing with business analysts

Integration testing with connected systems

Performance testing under peak loads

## Financial Summary

### Year 1 Costs

Implementation: $1,000,000 - $1,500,000

SaaS Licensing: $825,000

Partner Support: $100,000

Total Year 1:: $1,925,000 - $2,425,000

### Ongoing Annual Costs (Year 2+)

SaaS Licensing: $825,000

Partner Support: $100,000

Total Annual:: $925,000

### Current Annual Costs

On-Premise Licensing: $547,000

Partner Support (Lightwell): $230,000

Hardware (amortized): ~$500,000 - $600,000

Total Current:: $1,277,000 - $1,377,000

### Net Annual Savings

Estimated:: $125,000 - $450,000/year (depending on actual hardware costs)

ROI Period:: 3-5 years to recover implementation costs

## Recommendations

**Immediate Actions**

Resolve current web.xml deployment issues with Lightwell

Gather accurate hardware and infrastructure costs

Validate actual order line volumes for licensing

**Decision Timeline**

Complete detailed scoping by end of June

Make go/no-go decision by mid-July

Allow 2 weeks for contract negotiations before September 1st renewal

**Risk Mitigation**

Negotiate fixed-price implementation contract

Establish clear rollback criteria and process

Maintain on-premise environment during 1-year evaluation

**Future Considerations**

Defer Store module and SIP until post-stabilization (Year 2)

Plan for functional analyst training on cloud platform

Evaluate alternative partner options for ongoing support

## Open Questions

What are the exact hardware costs (purchase + maintenance)?

What is the actual annual order line volume trend?

Which customizations are business-critical vs. nice-to-have?

What are the integration dependencies with other systems?

Can implementation be scoped to lower end of $1M estimate?

What are the specific SLAs and support terms in SaaS contract?

## Next Steps

Schedule technical deep-dive with IBM Expert Labs and Jim (technical lead)

Compile list of questions for Lightwell regarding current issues

Obtain detailed hardware cost breakdown from infrastructure team

Review last 12 months of Lightwell invoices for accurate support costs

Engage Kathy and Tony in upcoming technical calls

Develop formal proposal with detailed scope and pricing